## GPI-Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Student Insights : A Python Approach
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE
EXPECTED COMPLETION DATE
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | I analyzed the relationship between students’ economic background, academic performance, skills, and expected salary using Python. I performed data cleaning, exploratory data analysis, and visualization to find meaningful insights.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Most of students do not have a clear understanding of how their academic performance, skills, and economic background affect their career outcomes and expected salary. Through this project, I used a data-driven approach to analyze student data and identify relationships between important variables like GPA, income, experience, and expected salary. This analysis helps in better understanding these factors and supports informed decision-making for career planning.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | I completed the analysis using Python libraries like Pandas, Matplotlib, and Seaborn. The project was evaluated based on insights generated, relationships identified, and visualizations created.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Cleaned dataset and Python (google Notebook) analysis Visualizations showing relationships between key factors Clear insights on factors affecting expected salary Final report summarizing findings
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Data collection and input handling Data cleaning and preprocessing Exploratory data analysis and feature understanding Visualization of relationships between key variables
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | The initial version of the system, developed in Python using Jupyter Notebook, Integration with job portals or external APIs Real-time salary trend analysis Development of a mobile or web application Automatic resume generation Integration with external student databases
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Number of Team Members: 1 Project Developer: Abhishek Mitra – Responsible for Data collection, preprocessing, analysis, visualization, and testing.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop or computer system Python programming environment Python libraries (e.g., pandas, numpy, matplotlib, seaborn) Development tools such as Jupyter Notebook
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Estimated Costs: Development Cost: Software tools: Free (Open-source libraries)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Abhishek Mitra
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Project Guide Project Evaluation Committee
END CUSTOMER (Mention the client name.) | Primary Users: Students seeking career guidance Secondary Users: Educational institutions and career counselors
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Limited dataset size may affect the reliability of analytical insights. Inaccurate or inconsistent input data can lead to misleading predictions. Overfitting of the analytical model may reduce its generalizability to new data.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | The dataset used for analysis is accurate and trustworthy. Students are expected to provide correct information when using the system. The dataset includes sufficient features to support career prediction. Users will have access to a computer with an internet connection.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Project development time is limited. The quality of analysis depends on the dataset provided. Computational resources may be limited for extensive model training.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date : 01-18-2026 Requirement gathering is considered complete after submission of the SRS document.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date : 01-23-2026 Planning phase is completed after preparation of the Work Breakdown Structure (WBS), project schedule, and RAID logs.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date : 01-26-2026 Design stage is completed after submission of system design specifications and analysis workflow/visualization layouts.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date : 01-31-2026 Development is completed after implementation of data preprocessing, analysis, and visualization using Python in Jupyter Notebook.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date : 02-05-2026 Testing is completed after validating data analysis results, visualizations, and system outputs.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date : 02-08-2026 Deployment is completed after finalizing the Jupyter Notebook, outputs, and project documentation.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date : 02-11-2026 Project closure is completed after submission of the final report, lessons learned document, and user guide.