## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Abhishek Mitra
PROJECT NAME: | Visualizing Student Success : A Python Approach
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Data Analytics |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-11010
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 16-01-2026 | Initial difficulty in understanding project requirements during project start | Requirement Analysis | Yes | Conduct detailed requirement analysis before starting development | Reviewed problem statement and clarified project objectives | Project Intern | Solved | Clear understanding improved project workflow
2 | 2026-01-20 | Missing and inconsistent data identified in dataset | Data Quality | Yes | Perform data validation and cleaning at an early stage | Used Python (pandas) for data cleaning and preprocessing | Data Analyst | Solved | Data accuracy improved significantly
3 | 2026-01-24 | Incorrect outputs observed during data analysis and calculations | Technical / Development | Yes | Validate calculations and analysis using sample data | Re-tested Python code and corrected calculation logic | Data Analyst | Solved | Analysis results became accurate
4 | 2026-01-28 | Performance issues while processing large datasets | Performance | Yes | Optimize data processing and remove unnecessary columns | Optimized Python code and reduced unnecessary computations | Data Analyst | Solved | Processing time improved
5 | 2026-05-01 | Model results impacted due to inconsistent data patterns | Analytics / Modeling | Yes | Monitor data patterns and validate datasets regularly | Implemented data validation and consistency checks | Data Analyst | Monitoring | Regular monitoring required
6 | 2026-02-05 | Difficulty in understanding analysis results and visual outputs | Usability | No | Add clear labels, titles, and documentation for visualizations | Improved charts and added explanations for analysis results | Data Analyst | Solved | Better understanding of results
7 | 2026-02-10 | Time management challenges during final documentation phase | Project Management | Yes | Allocate buffer time for documentation work | Adjusted schedule and prioritized remaining tasks | Project Intern | Solved | Better time management learned
8 | 2026-02-15 | Minor formatting and editing errors in final report | Documentation | No | Review formatting and structure before submission | Performed final proofreading and corrections | Project Intern | Solved | Final report quality improved