## RAID log
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 1 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Data Analytics |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 2 | 0 | 0
[10 empty] | Issue | 1 | 0 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: |  | Project Team Lead: |  |  |  | Dependency | 3 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 5
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Slow execution of Python scripts when handling large datasets | Decreased efficiency and slower analytical processing | Refactor and optimize code for better performance | Data Analyst | Moderate | 9 | Open | Risk
2 | Risk | Model performance degradation due to data drift | Generated insights may lose accuracy over time | Monitor model performance metrics | Data Analyst | High | 16 | Open | Assumption
3 | Assumption | The dataset utilized is reliable and sufficiently complete | Analytical results are highly dependent on data integrity | Confirm dataset source and validate data before analysis | Project Manager | Moderate | 7 | Open | Issue
4 | Assumption | Stakeholders are capable of interpreting analytical outputs and visual reports | Possibility of incorrect interpretation of results | Provide proper documentation and explanations for graphs and analysis outputs | Data Analyst | Moderate | 8 | Open | Dependency
5 | Issue | Incomplete or missing entries in critical dataset attributes | Can reduce accuracy of analysis and predictions | Apply data cleaning techniques such as imputation or removing invalid records using pandas | Data Analyst | High | 14 | Open
6 | Dependency | Availability of essential Python packages and development setup | Project timeline may be impacted if tools are not accessible | Ensure required Python libraries and development environment are installed before starting the project | Project Manager | Moderate | 8 | Closed | Open
7 | Dependency | Timely updates from the data source | Delay in refreshing analytical results | Set a fixed schedule for dataset updates and refresh analysis periodically | Project Manager | Moderate | 10 | Closed | Closed
8 | Dependency | System capability and computational limitations | Slower processing and execution of scripts | Use optimized algorithms and ensure adequate system resources | Project Manager | Moderate | 9 | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24